## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Team Meeting 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Ma Xiao | Han Si Meng | He Yu Hao | Loh Yi Xuan Renice | Yeoh Jun Yi
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited
1 | System Requirement Sepcification Task assignment: Problem Statement: Han Si Meng Overview: Han Si Meng Investigation and Analysis Methodology: He Yu Hao Constraints: He Yu Hao Operational Requirements: Ma Xiao Funtaional Requirements: Ma Xiao Input Requirements: Loh Yi Xuan Renice Process Requirements: Loh Yi Xuan Renice Output Requirements: Loh Yi Xuan Renice Hardware Requirements: Yeoh Jun Yi Software Requirements: Yeoh Jun Yi Deployment Requirements: Han Si Meng | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 10 | 8 | 14 | Ma Xiao | He Yu Hao Han Si Meng Loh Yi Xuan Renice Yeoh Jun Yi | Through Discussion | Yes | 14 | Excited | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 14 | 14 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 7 | 7 | 7
2 | Quality Plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 5.6 | 14 | Loh Yi Xuan Renice | Yeoh Jun Yi | Through Discussion | Yes | 14 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 14 | 14 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 9
3 | Database Design | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 6.4 | 2 | He Yu Hao | Ma Xiao Yeoh Jun Yi | Through Discussion | Yes | 2 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 6 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 9 | 10
4 | Learning Firebase | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 5.8 | 4.6 | 14 | He Yu Hao | Ma Xiao Yeoh Jun Yi | Allocated by Team Leader | Yes | 14 | Excited | 10
| Estimated Task Priority（0-10） |  | 6 | 6 | 7 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 5 | 4 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 14 | 14 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10
5 | Client Application Home Page Development | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 10 | 8.6 | 3 | Han Si Meng |  | Through Discussion | Yes | 3 | Excited | 9.6
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 8 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 3 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 | 9 | 9
6 | Deliveryman Application Development | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 9 | 7.2 | 7 | 2.4 | Ma Xiao | Han Si Meng | Through Discussion | Yes | 3 | Excited | 9.4
| Estimated Task Priority（0-10） |  | 7 | 7 | 8 | 6 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 6 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 9 | 8 | 8
7 | Client Application Restaurant Page Development | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 10 | 10 | 9.6 | 8.2 | 3.6 | Han Si Meng |  | Through Discussion | Yes | 2 | Excited | 9.4
| Estimated Task Priority（0-10） |  | 9 | 10 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 9 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 3 | 3 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 9
8 | Firebase Setup and insert test data | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.4 | 2 | He Yu Hao | Ma Xiao Yeoh Jun Yi | Allocated by Team Leader | Yes | 2 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 9 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10
9 |  | Task Quality Evaluation (After Task Completed) | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)