## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Team Meeting 3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Ma Xiao | Han Si Meng | He Yu Hao | Loh Yi Xuan Renice | Yeoh Jun Yi
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited
1 | Project Plan Task assignment: Introcuction: Ma Xiao Project Organization: Ma Xiao Process Definition: He Yu Hao Schedule: He Yu Hao, Ma Xiao Project Esitmates: Ma Xiao Project Checklist: Ma Xiao Best Practice Checklist: Han Si Meng Risk Management: Loh Yi Xuan Renice, Yeoh Jun Yi Quality Assurance: Loh Yi Xuan Renice, Yeoh Jun Yi Monitoring and Control: Ma Xiao | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 10 | 8 | 14 | Ma Xiao | He Yu Hao Han Si Meng Loh Yi Xuan Renice Yeoh Jun Yi | Through Discussion | Yes | 14 | Excited | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 14 | 14 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 7 | 7 | 7
2 | Risk Management | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 5.6 | 14 | Loh Yi Xuan Renice | Yeoh Jun Yi | Through Discussion | Yes | 14 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 14 | 14 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 9
3 | Database Set up | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 6.4 | 2 | He Yu Hao | Ma Xiao Yeoh Jun Yi | Allocated by Team Leader | Yes | 2 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 6 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 9 | 10
4 | Client Application Display Cart Page | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 5.8 | 4.6 | 14 | Han Si Meng |  | Allocated by Team Leader | Yes | 14 | Excited | 10
| Estimated Task Priority（0-10） |  | 6 | 6 | 7 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 5 | 4 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 14 | 14 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10
5 | Client Application Add to Cart Function | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 9 | 8.6 | 3 | Han Si Meng |  | Allocated by Team Leader | Yes | 3 | Excited | 9.6
| Estimated Task Priority（0-10） |  | 10 | 9 | 10 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 8 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 3 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 | 9 | 9
6 | Deliveryman Application Order Status Update | Task Quality Evaluation (After Task Completed) | 8 | 10 | 9 | 9 | 9 | 7.4 | 7 | 2.6 | Ma Xiao |  | Allocated by Team Leader | Yes | 3 | Excited | 9
| Estimated Task Priority（0-10） |  | 7 | 8 | 8 | 6 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 6 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 2 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 9 | 8 | 8
7 | Client Application Restaurant Page Development | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 10 | 9.6 | 8.2 | 3.6 | Han Si Meng |  | Allocated by Team Leader | Yes | 2 | Excited | 9.6
| Estimated Task Priority（0-10） |  | 9 | 10 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 9 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 3 | 3 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 9
8 | Firebase Conncetion with the Application | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.4 | 2 | He Yu Hao | Ma Xiao | Allocated by Team Leader | Yes | 2 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 9 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10
9 | Vendor Application Check Orders Page | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 | 9 | 9 | 8.6 | 7.4 | 3.4 | Yeoh Jun Yi | Ma Xiao Loh Yi Xuan Renice | Allocated by Team Leader | Yes | 4 | Excited | 8.6
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 8 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 4 | 3 | 4
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)