## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Team Backlog 5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Ma Xiao | Han Si Meng | He Yu Hao | Loh Yi Xuan Renice | Yeoh Jun Yi
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited
1 | Test Client Application, including: - Log in with Google OAuth - Display Restaurants - Display Promotions - Display Restaurant Dishes - Add to Cart - Place Order - View Profile - View Order History | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9.6 | 7.4 | 2.8 | Ma Xiao | Han Si Meng He Yu Hao | Through Discussion | Yes | 3 | Excited | 9
| Estimated Task Priority（0-10） |  | 8 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 6 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 7 | 10 | 7
2 | Test Deliveryman Application, including: - Log in with Google OAuth - Order Status Display and Update - View Profile | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 5.6 | 3 | Han Si Meng | Ma Xiao He Yu Hao | Through Discussion | Yes | 4 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 2 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 9
3 | Test Vendor Application, including: - Log in with Google OAuth - Confirm Order - Reject Order - View Profile - View Restaurant | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 9.6 | 6.4 | 2 | Han Si Meng | Ma Xiao He Yu Hao | Through Discussion | Yes | 1 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 8 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 6 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 9 | 10
4 | CMMI1.3 Level2 Definition Outline | Task Quality Evaluation (After Task Completed) | 10 | 9 | 10 | 10 | 9 | 8.8 | 8.4 | 2.6 | Loh Yi Xuan Renice | Ma Xiao Yeoh Jun Yi | Allocated by Team Leader | Yes | 3 | Excited | 9.6
| Estimated Task Priority（0-10） |  | 10 | 10 | 8 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 7 | 9 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 3 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 9 | 10
5 | Test Plan | Task Quality Evaluation (After Task Completed) | 8 | 10 | 9 | 9 | 10 | 9.4 | 8 | 7.8 | He Yu Hao | Yeoh Jun Yi Loh Yi Xuan Renice | Allocated by Team Leader | Yes | 9 | Excited | 9.2
| Estimated Task Priority（0-10） |  | 10 | 9 | 10 | 8 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 9 | 8 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 7 | 7 | 7
6 | Test cases and Requirements Test Coverage Report | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 10 | 7 | 8.6 | Han Si Meng | Ma Xiao He Yu Hao | Allocated by Team Leader | Yes | 9 | Excited | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 8 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 10 | 9 | 9 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 7 | 8 | 8
7 | Presentation Slides | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 5.6 | 7 | Yeoh Jun Yi | Ma Xiao He Yu Hao Han Si Meng Loh Yi Xuan Renice | Allocated by Team Leader | Yes | 9 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 6 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 9
8 | Code revision | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 5.6 | 7.2 | Ma Xiao | He Yu Hao Han Si Meng | Allocated by Team Leader | Yes | 8 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 5 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 8 | 6 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 8 | 9